## Formats 1
INVOICE FORMATS
Front Page
JBPB_C10 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | CONTRACT AMOUNT | TOTAL COMPLETED TO DATE |  | PREVIOUS APPLICATION |  | THIS APPLICATION |  | CONTRACT BALANCE | HOLDBACK
[5 empty] | AMOUNT | % | AMOUNT | % | AMOUNT | %
% For Total, Previous and Current Complete
JBPB_C11 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  |  | WORK COMPLETED |  | WORK COMPLETED TO DATE | PER-% | BALANCE TO FINISH | TOTAL HOLDBACK TO DATE |  |  |  | CHANGE ORDER SUMMARY
|  |  |  | ORIGINAL | CHANGE ORDERS | CURRENT | FROM PREVIOUS INVOICES | INVOICED THIS PERIOD
INCLUDES CHANGE ORDER SUMMARY PAGE, Change Order in Detail Section
JBPB_C11PW | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  |  | WORK COMPLETED |  | WORK COMPLETED TO DATE | PER-% | BALANCE TO FINISH | TOTAL HOLDBACK TO DATE
|  |  |  | ORIGINAL | CHANGE ORDERS | CURRENT | PREVIOUSLY BILLED | INVOICED THIS PERIOD
Includes Change Orders
JBPB_C12 | COLUMNS | Bill Code | Description | Amount | Previous Progress | This Progress | Complete To Date | % | Balance
Change Orders, Taxes
JBPB_U10 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  |  | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER- % | BALANCE TO FINISH | RETAINAGE
[7 empty] | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Material Stored
JBPB_U11 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  |  | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER- % | BALANCE TO FINISH | RETAINAGE
|  |  |  | ORIGINAL | CHANGE ORDERS | CURRENT | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Change Orders and Material Stored.
JBPB_U11CM | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  |  |  | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER- % | BALANCE TO FINISH | RETAINAGE
|  |  |  | ORIGINAL | CHANGE ORDERS | BUDGET TRANSFER CHANGE ORDERS | CURRENT | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Change Orders, Trasfer Change Orders Separately, Material Stored
JBPB_U11PA | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  |  | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER- % | BALANCE TO FINISH | RETAINAGE
|  |  |  | ORIGINAL | CHANGE ORDERS | CURRENT | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Change Orders and Material Stored
JBPB_U12 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE |  | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL TAXES TO DATE | TOTAL COMPLETED AND STORED TO DATE | PER- % | BALANCE TO FINISH | RETAINAGE
[6 empty] | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Material Stored, Total Taxes
JBPB_U15 | COLUMNS | ITEM NO. | DECRIPTION OF WORK | ORIGINAL SOV | SOV CHANGES | SCHEDULED VALUE | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER- %(I/E) | BALANCE TO FINISH | RETAINAGE
[7 empty] | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Change Orders, Material Stored
JBPB_U16 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER- % | BALANCE TO FINISH | THIS PERIOD RETAINAGE | RETAINAGE
[5 empty] | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Material Stored, Retainage this Period and Total Retaiage
JBPB_U17 | COLUMNS | ITEM NO. | DESCRIPTION OF WORK | ORIGINAL SOV | SOV CHANGES | SCHEDULED VALUE | WORK COMPLETED |  | MATERIAL PRESENTLY STORED | TOTAL COMPLETED AND STORED TO DATE | PER-% | BALANCE TO FINISH | THIS PERIOD RETAINAGE | RETAINAGE
[7 empty] | FROM PREVIOUS APPLICATION | THIS PERIOD
Shows Change Orders, Material Stored, Retainage this Period and Total Retainage

## Formats 2
INVOICE FORMATS |  |  |  |  | Additional/new formats are added here, JBPB_C10 is noted here again for reference
JBPB_C10 |  | ITEM NO. | DESCRIPTION OF WORK | CONTRACT AMOUNT | TOTAL COMPLETED TO DATE |  | PREVIOUS APPLICATION |  | THIS APPLICATION |  | CONTRACT BALANCE | HOLDBACK
[5 empty] | AMOUNT | % | AMOUNT | % | AMOUNT | %
% For Total, Previous and Current Complete
JBPB_C10Q |  | ITEM NO. | DESCRIPTION OF WORK | Quantity | Unit | Unit Price | Contract Amount | Total Completed to Date |  | Previous Application |  | This Application
[8 empty] | Amount | % | Amount | % | Amount | %
Quantity, Unit, Unit Price
JBPB_C11PC |  | Item No. | Description of Work | Original Scheduled Value | Work Completed |  | Work Completed to Date | Per (%) | Balance to Finish | Total Holdback to Date
[5 empty] | Previously Billed | Invoiced this Period
JBPB_CORE1 |  | Item | Description | Qty | Unit | Unit Price $ | Estimated Amount $ | Quantities | [5 empty] | Retainage
[8 empty] | Previous | Current | To Date | Previous $ | Current $ | To Date $
Notes: Unit, Price, Quantity, Estimated Amount
JBPB_HLDBK |  | PB Draw# | Invoice No. |  | Total Holdback
Notes: Only Shows Retainage Amount including Tax.
JBPB_U10CR |  | Item No. | Description of Work | Scheduled Value | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage
[5 empty] | From Previous Application | This Period | [8 empty] | This is the first page printed before header. | Change Order page when "PCI Detail Billing" flag is unchecked for the contract | Change Order listing when "PCI Detail Billing" flag is checked for the contract
Notes: Shows Material Stored. Change Order in header by addition and deduction. Change Order page had different layout based on the 'PCI Detail Billing' flag. Allows partial billings of PCIs
JBPB_U10OC |  | Item No. | Description of Work | Original Budget | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage
[5 empty] | From Previous Application | This Period
Notes: Shows Original Budget and PCIs list.
JBPB_U10Q |  | Item No. | Description of Work | Scheduled Value | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage
[5 empty] | From Previous Application | This Period
Notes: Shows Material Stored.
JBPB_U10Q2 |  | Item | Description | Qty | Unit | Unit Price $ | Total Contract Amount | Previous Completed |  | This Period |  | Completed To Date |  | % Compl
[8 empty] | Units | Amount | Units | Amount | Units | Amount
Notes: Request For Payment Detail
JBPB_U10SC |  | Item No. | Description of Work | Subcontractor | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage
[5 empty] | From Previous Application | This Period
Notes: Sworn Statement, Subcontractor, Material Stored
JBPB_U10TR |  | Item No. | Description of Work | Scheduled Value | Transfer Budget Amounts | Revised Scheduled Vallue | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage
[7 empty] | From Previous Application | This Period
Notes: Includes Transfer Budget Amount, Revised Scheduled Vaue, OCO, PCI List
JBPB_U11VN |  | Item No. | Description of Work | Scheduled Value |  |  | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage | Net Amount Due
|  |  |  | Original | Change Orders | Current | From Previous Application | This Period
Notes: Vendor Name, Change Orders, Net Amount Due
JBPB_U13 |  | Item No. | Description of Work | Scheduled Value | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage
[5 empty] | From Previous Application | This Period
Notes: Change Order Summary, Change Order Previous Months, Material Stored
JBPB_U14 |  | Item No. | Description of Work | Scheduled Value | Subcontractor Detail |  | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | % Completed vs Buyout | Balance to Finish vs Buy-out Amount | Retainage
[5 empty] | Name | Buy-Out Amount | From Previous Application | This Period
Notes: Subcontractor Detail including Name and Buy-out Amount; % completed vs buyout, Balance to Finish compared to Buy-out Amount.
JBPB_U15PB |  | Item No. | Description of Work | Original SOV | SOV Changes | Scheduled Value | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % | Balance to Finish | Retainage
[7 empty] | From Previous Application | This Period
Notes: Different invoices for groupings, includes Change Orders, Material Stored
JBPB_U19 |  | Job Name | Original Contract | Approved Changes | Revised Contract | Committed Obligations | Previously Invoiced | Current Gross | Current Retention | Completed to Date | Comp % | Retention to Date | Ret %
Notes: Requisition Report. Includes Revised GMP.
JBPB_U20 |  | Item No. | Description of Work | Scheduled Value |  |  | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % (G/C) | Balance to Finish | Retainage Released This Period | Retainage
|  |  |  | Original | Change Orders | Current | From Previous Application | This Period
Notes: Change Orders, Material Stored, Retainage Released.
JBPB_U21 |  | Item No. | Description of Work | Scheduled Value |  |  |  | Work Completed |  | Material Presently Stored | Total Completed and Stored to Date | Per % | Balance to Finish | Retainage
|  |  |  | Original | Change Orders | Budget Transfer Change Orders | Current | From Previous Application | This Period
Notes: Change Orders, Budget Transfer Change Orders, Material Stored.
JBPB_U23 | Description | Scheduled Value | Prev App Value | This App Value Completed | Total Value | Total % Complete | Balance To Finish
Notes: Change Orders Page, includes Tax in Header.
JBPHS_TYPE
Notes: Includes phase level and reimbursements.

## Free Form
Free Form Invoices
JBINVPRT | Total to Date | Previously Billed | Currently Billed
Notes:
JBINVPRT2
JBINVPRT3 | Description | Amount
Subtotal
Holdback
Sales Tax
Balance Due